## Sheet1
Here we are | week | Date fra | Date til | Planned Tasks | Writing Tasks
x | Week 06 | February 5, 2024 | February 11, 2024 | Data input | Introduction
| Week 07 | February 12, 2024 | February 18, 2024 | Data input | Introduction
| Week 08 | February 19, 2024 | February 25, 2024 | Algorithm, previous work | Relevant theory
| Week 09 | February 26, 2024 | March 3, 2024 | Algorithm, previous work | Relevant theory
| Week 10 | March 4, 2024 | March 10, 2024 | Test and implementation - existing methods | Methodology
| Week 11 | March 11, 2024 | March 17, 2024 | Test and implementation - existing methods | Methodology
| Week 12 | March 18, 2024 | March 24, 2024 | Test and implementation - new approaches | Methodology
| Week 13 | March 25, 2024 | March 31, 2024 | Test and implementation - new approaches | Methodology
| Week 14 | April 1, 2024 | April 7, 2024 | Test and implementation - new approaches | Result
| Week 15 | April 8, 2024 | April 14, 2024 | Test and implementation - new approaches | Result
| Week 16 | April 15, 2024 | April 21, 2024 | Interpretation & performance evaluation | Result
| Week 17 | April 22, 2024 | April 28, 2024 | Interpretation & performance evaluation | Result
| Week 18 | April 29, 2024 | May 5, 2024 | Interpretation & performance evaluation | Conclusion
| Week 19 | May 6, 2024 | May 12, 2024 |  | Revision
| Week 20 | May 13, 2024 | May 19, 2024 |  | Revision
| Week 21 | May 20, 2024 | May 26, 2024 |  | Revision
| Week 22 | May 27, 2024 | June 2, 2024 |  | Revision
| Week 23 | June 3, 2024 | June 9, 2024 |  | Revision
| Week 24 | June 10, 2024 | June 15, 2024 - 14.00 |  | Final submission
In total: 19 weeks
Thesis submission as a PDF file only, with maximum 1 GB